## Sheet1
USER STORIES |  | # PRJ-PM113
JumLit |  | AS OF YYYY-MM-DD
ID | User Story | Priority | Assignee | Estimate | Status
1 | As a user, I want to be able to register with my email and password, so that I can sign up in the system | 1 | Ковалев Семикин Селех | 10 | Closed
2 | As a user, I want to be able to log into my account using my email and password, so that I can start working | 1 | Ковалев Семикин Селех | 7 | Closed
3 | As a user, I want to be able to set my additional user details so that other users can view them and verify me. | 1 | Ковалев Семикин Селех | 5 | Closed
4 | As a user, I want to be able to edit my additional user details so that they are always up to date. (login + email) | 1 | Ковалев Семикин Селех | 6 | Open
5 | As a user, I want to be able to create a diagram and become it's owner so that I can start working on the diagram. | 1 | Ковалев Семикин Селех | 10 | Closed
6 | As a diagram owner, I want to be able to add new members to the project so that they become project members and can work on a diagram. | 1 | Ковалев Семикин Селех | 5 | Closed
7 | As a user, I want to be able to view all the diagrams I take part in, so that i can switch the one that I am currently working on and to know what diagrams do i participate in. | 1 | Ковалев Семикин Селех | 4 | Closed
8 | As a diagram owner, I want to be able to enter and edit the diagram details, so that it is possible to distinguish between different diagrams. | 1 | Ковалев Семикин Селех | 4 | Closed
9 | As a diagram owner, I want to be able to delete the project, so that it won’t be in the system when it is no longer needed. | 1 | Ковалев Семикин Селех | 3 | Closed
10 | As a collaborator, I want the system to save changes using button | 1 | Ковалев Семикин Селех | 4 | Rejected
11 | As a collaborator, I want to be able to open the diagram editor, so that I can have access to the diagram creation tools. | 1 | Ковалев Семикин Селех | 3 | Closed
12 | As a collaborator, I want to be able to add, rename and remove classes to the diagram. | 1 | Ковалев Семикин Селех | 2 | Closed
13 | As a collaborator, I want to be able to add class members as a list in a class rectangle. | 1 | Ковалев Семикин Селех | 5 | Closed
14 | As a collaborator, I want to be able to add, edit, remove class attributes. | 1 | Ковалев Семикин Селех | 5 | Closed
15 | As a collaborator, I want to be able to add, edit, remove class methods. | 1 | Ковалев Семикин Селех | 3 | Closed
16 | As a collaborator, I want to be able to set class and class members visibility. | 1 | Ковалев Семикин Селех | 1 | Closed
17 | As a user, I want to be able to get email notifications when I am invited to the team to work on a project. | 5 | Ковалев Семикин Селех | 1 | Closed
18 | As a diagram owner, I want to have private diagrams (503 forbidden) | 3 | Ковалев Семикин Селех | 4 | Closed
19 | As a collaborator, I want to be able to add a dependency relationship between classes. | 3 | Ковалев Семикин Селех | 1 | Closed
20 | As a collaborator, I want to be able to add an association relationship between classes as a line between them. | 3 | Ковалев Семикин Селех | 1 | Closed
21 | As a collaborator, I want to be able to link any number of classes with an association. | 3 | Ковалев Семикин Селех | 3 | Closed
22 | As a collaborator, I want to be able to name association relationships. | 3 | Ковалев Семикин Селех | 1 | Closed
23 | As a collaborator, I want to be able to adorn ends of an association line with role names, ownership indicators, multiplicity, visibility and other properties. | 3 | Ковалев Семикин Селех | 1 | Closed
24 | As a collaborator, I want to be able to set the direction of the association relationship (either a uni- or bi-directional). | 3 | Ковалев Семикин Селех | 1 | Open
25 | As a collaborator, I want to be able to add an aggregation relationship between two classes as a line with a rhombus. | 3 | Ковалев Семикин Селех | 2 | Closed
26 | As a collaborator, I want to be able to adorn ends of an aggregation line with role names, ownership indicators, multiplicity, visibility and other properties. | 3 | Ковалев Семикин Селех | 1 | Closed
27 | As a collaborator, I want to be able to name aggregation relationships. | 3 | Ковалев Семикин Селех | 1 | Closed
28 | As a collaborator, I want to be able to add a composition relationship as a line with a filled diamond shape. | 3 | Ковалев Семикин Селех | 1 | Closed
29 | As a collaborator, I want to be able to name aggregation relationships. | 3 | Ковалев Семикин Селех | 1 | Closed
30 | As a collaborator, I want to be able to adorn ends of a composition line with role names, ownership indicators, multiplicity, visibility and other properties. | 3 | Ковалев Семикин Селех | 2 | Rejected
31 | As a collaborator, I want to be able to add a generalization relationship between classes as a line with a hollow triangular shape. | 3 | Ковалев Семикин Селех | 1 | Closed
32 | As a collaborator, I want to be able to set the direction of a generalization relationship. | 3 | Ковалев Семикин Селех | 1 | Closed
33 | As a collaborator, I want to be able to add a realization relationship between classes as a dashed line with a hollow triangle. | 3 | Ковалев Семикин Селех | 0.5 | Closed
34 | As a collaborator, I want to be able to set the class on a diagram to be an entity and to be displayed as a circle. | 2 | Ковалев Семикин Селех | 1 | Rejected
35 | As a collaborator, I want to be able to save a diagram as a PNG image. | 5 | Ковалев Семикин Селех | 2 | Closed
36 | As a collaborator, I want to be able to export a diagram, to an XML-file. | 4 | Ковалев Семикин Селех | 3 | Rejected
37 | As a collaborator, I want to be able to select an XML file on the system to import the diagram | 4 | Ковалев Семикин Селех | 5 | Rejected
38 | As a collaborator, I want to be able to generate Java-classes with all relationships using the information from the diagram. | 4 | Ковалев Семикин Селех | 10 | Closed
39 | As a collaborator, I want to be able to download the generated Java-classes as an archive. | 3 | Ковалев Семикин Селех | 12 | Closed
40 | As a collaborator, I want to be able to comment different elements of the diagram and see comments of other teammates. | 3 | Ковалев Семикин Селех | 5 | Closed
41 | As a collaborator, I want to see all other members of the project | 3 | Ковалев Семикин Селех | 5 | Closed
42
43
44
45
46
47
48
49
50
51